## Sheet1
Task | Start Date | End Date | Duration
Brainstrom Ideas for Website | 2020-02-20 | 2020-02-25 | 5
Create Schedule | 2020-02-21 | 2020-02-25 | 4
Create Use Case | 2020-02-21 | 2020-02-25 | 4
Fill-out Requirements | 2020-02-21 | 2020-02-25 | 4
Start SPMP | 2020-02-22 | 2020-02-25 | 3
Meet up with Professor | 2020-02-25 | 2020-02-25 | 1
Begin creating Website | 2020-02-25 | 2020-02-26 | 1
Look into themes and plugins | 2020-02-25 | 2020-02-28 | 3
Create three forms | 2020-02-28 | 2020-02-29 | 1
Show a Calendar with Reconditioning events | 2020-02-29 | 2020-03-02 | 2
Orangize website (tabs, widgets, videos, page functionality) | 2020-03-02 | 2020-03-25 | 23
Explanation of Reconditioning Session page | 2020-03-02 | 2020-03-10 | 8
Subscribe to newsletter section | 2020-03-05 | 2020-03-08 | 3
TU logo/EduCycle Logo | 2020-03-05 | 2020-03-06 | 1
Continue reoreganizing webstie (edit things that were previously done) | 2020-03-10 | 2020-03-25 | 15
Testing of Website and Re-check Requirements up to this point | 2020-03-25 | 2020-04-01 | 7
Update SPMP, Gantt Chart, | 2020-03-25 | 2020-04-01 | 7
Create a Q and A section | 2020-04-01 | 2020-04-10 | 9
Create a page for Staff that is in charge | 2020-04-02 | 2020-04-03 | 1
Insert types of computers/hardware EduCycle has | 2020-04-02 | 2020-04-03 | 1
create a database for EduCycle Inventory | 2020-04-09 | 2020-04-10 | 1
Allow TU Student employees log in | 2020-04-09 | 2020-04-10 | 1
Request computer form should be forwarded to EduCycle Email | 2020-04-09 | 2020-04-10 | 1
Check to see if system can be on moble, tablet, multiple browsers | 2020-04-08 | 2020-04-09 | 1
Find quotes given by past Teachers, faculity, and staff | 2020-04-03 | 2020-04-05 | 2
Create a motto with Julie leary | 2020-04-06 | 2020-04-06 | 1
Testing of Requirements | 2020-04-10 | 2020-04-15 | 5
Update SPMP | 2020-04-11 | 2020-04-15 | 4
https://www.workzone.com/blog/gantt-chart-excel/