## Sheet1
Milestones | Due Date | Date Completed | Notes
Requirement Document | 2020-02-25 | 2020-02-25 | Completed before the Design Review Meeting with Broadwater
Use Cases | 2020-02-25 | 2020-02-25 | Completed before the Design Review Meeting with Broadwater
Repo Setup | 2020-02-25 | 2020-02-25 | Completed before the Design Review Meeting with Broadwater
SPMP | 2020-05-01 | 2020-04-25 | Completed and uploaded to Blackboard, if rejected, then I will make edits
Create a simple website that has three forms | 2/30/2020 | 2/30/2020 | Completed with the help of Julie Leary (Provided information needed for each form)
Form#1 Request a computer | 2/30/2020 | 2/30/2020
Form#2 Volunteering | 2/30/2020 | 2/30/2020
Form#3 Request a reconditioning session | 2/30/2020 | 2/30/2020
Mid-Semester review (w/ Julie Leary) | 2020-04-07 | 2020-04-21 | Due to CoronaVirus, Julie Leary's schedule became busy and constant rescheduling occurred. Instead of meeting physically, we met in a WebEx meeting two weeks after the original date
Connect Database to Website | 2020-04-12 | 2020-04-09 | Completed. HOWEVER discussed with Broadwater and need to connect to real database. Not my pre-test database
Beta Test | 2020-04-29 | TBA | Going to send over to Julie Leary and she will have some of her employees look over and test some of the functions
Project Presentation | 2020-05-05 | TBA | Created a powerpoint for the presentation
Present to EduCycle Coordinator (Julie Leary) | TBA | TBA